## Form 5 - AGDAR
FDP Form 5 - Annual GAD Accomplishment Report
(PCW-DILG-DBM-NEDA JMC No. 2016-01 dated January 12, 2016, Annex E)
ANNUAL GENDER AND DEVELOPMENT (GAD) ACCOMPLISHMENT REPORT
FY 2021
Region: VII | [5 empty] | Total LGU Budget: P 275,589,442.46
Province: Ngeros Oriental | [5 empty] | Total GAD Expenditure:P 3,103,691.15
City or Municipality:Mabinay
Gender Issue or GAD Mandate (1) | GAD Objective (2) | Relevant LGU Program or Project (3) | GAD Activity (4) | Performance Indicator and Target (5) | Actual Results (6) | Approved GAD Budget (7) | Actual Cost or GAD Expenditure (8) | Variance or Remarks (9)
CLIENT-FOCUSED
1.Lack of facility to accomodate clients/personnel bringing 0-4 children while doing transaction in the clustered educational institutions of Mabinay 3 & 4 | To provide nursing mothers convenient, safe and secure area for breastfeeding. To provide a secure place for minding 0-4 year old children while parents/guardians are transacting business in the clustered educational instituitions of Mabinay 3 &4. | Provition of Wellnes Area and Child-Minding Center | Const. Of 2 Child-Minding Centers w/ a Built in wellness area for nursing mothers | Child Minding Centers w/ a built in wellness area for nursing mothers conctructed in Mabinay 3 & 4 by the end of Dec. 2021 to provide the aforementioned clients care and convenience | There was a change in location thru a resolution due to typographical errors. Thus documents on process for bidding | 1200000 | 0 | 0%
2. Absence of staff to provide temporary care and attention to children of working parents/clients while transacting business in Mabinay dist. 3 & 4 | To address the physical needs of children temporarily entrusted in the minding center | Hiring of personnel | Hiring a personnel to man the minding center | Personnel hired by the end of March, 2020 to man the mnding centers of Mabinay 3 & 4 | Un implemented | 50000 | 21890 | 43%
3.Sanitation Problem 500 Households have no access to sanitary toilets | To provide latrines to 500HH | Zero Open Defecation (ZOD) Program | Purch. Of 500 latrines | 500 Households provided sanitary toilets or latrines by the end of Dec. 2021 | 60 HH availed the provision of latrines | 300000 | 89000 | 30%
4. Inadequate Family Planning supplies for women of reproductive age | Provided adequate family supplies to women of reproductive age | Family Planning Program | Purch.of pills, depo, and IUD | 300 Women of reproductive age given adequate family planning supplies | 513 women provided family planning supplies | 200000 | 154033.5 | 70%
5. Inadequate suppliment for pregnant women | To adequately provide suppliments for pregnant women thus preventing maternal complications | Maternal Health | Purhase the neede suppliments for pregnant women | *200 Pregnant women given suppliments | 128 pregnant women given suppliments | 150000 | 102000 | 68%
6. Need to capacitate marginalized sectors on Anti-VAWC and other Gender related laws,(Women Asso.. Brgy. VAWC Desk DCW's & Pantawid Leaders) | To raise awareness and increase knowledge of marginalized sectors on VAWC and other GAD related Laws | Capacity Development | Conduct training workshops/seminars on: | 50 women's asso. Member | 31% implemented due to pandemic restrictions | 150000 | 45770 | 31%
32 VAW-Desk Officers
|  |  | -GST Orientation | 80 DCWs
|  |  | -Gender & CCCM/DRRM | 75 Parent Leaders, have undergone trainings and become aware on GAD related Laws,RA9262 & Magna Carta of Women
VAWC & other related Laws
|  |  | Women's month celebration |  |  | 150000 | 1880 | 1%
7 Lack of access of indigent Women and their Family to Social protection programs of LGU on Health,Social Welfare Services,VAWC & other special laws | To increase and sustain access of indigent women and family to Social protection programs. | Social Welfare and Development Programs | Provision of Financial assistance to individuals & Family in crises situation. | 350 individuals/family given financial assistance @ 2K by end of Dec. 2021 | 350 indigent individuals/families availed the financial assistance | 700000 | 684965 | 98%
8. Inadequate effort to address the issue of violence against children and women in ht eagency and communities. | To provide legal and psychosocial services to the victims of violence | Social Welfare and Development Programs | Provision of financial assistance to 40 VAW victims, vulnerable sectors and their family for the legal and psychosocial services | 40VAW victims and other vulnerable sectors and their family availed legal and Psychosocial services by end of Dec 2021. | women victims were refered to GWAVE | 50000 | 0 | 0%
9. Lack of financial support to VAWC,TIP victims, Solo Parents & displaced OFW's | To provide FA to VAWC,TIP victims,SP & displaced OFW's | Social Welfare and Development Programs | Extend Financial Assistance VAWC victims, Solo Parents,Trafficked in Persons & displaced OFW | 60 VAWC Victims @ 2,000.00K | 100% implemented | 100000 | 50500 | 51%
|  |  |  | 40 TIP Victims @ 2,500.00K | not yet implemented | 100000 | 0 | 0%
|  |  |  | 84 Displced OFW @ 3,000.00K | 100% implemented | 250000 | 104500 | 40%
|  |  |  | 170 solo Parents @ 1,500.00K extended financial support by end of Dec., 2021. | 100% implemented | 350000 | 362000 | 75%
10. Lack of opportunities for female women members and other vulnerable sectors to earn and augment family income | To provide Capital to identified women and other vulnerable sectors living belo poverty line. | Social Welfare and Development Programs | Provide Capital assistance to identified beneficiaries. | 6 Women's Associations @ 3,000.00/qualified member | for implementation | 500000 | 0 | 0%
|  |  |  | Women's Asso. In Brgys. TARA, POBLACION, LUMB.BANBAN. HAGTU, & Brgy. CANSAL-ING |  | 500000 | 0 | 0%
Livelihood Asso. In Brgys. BANban, Arebasore, Bulwang, Abis, Napasu-an & Brgy. Dahile.
11. Lack of awarenes among mothers and fathers for reesponsible parenthood | To conduct awareness & general concept on Responsible parethood/PES, family Dev.Services | Social Welfare and Development Programs | Organized & conduct of training on the ff: | 80 Day care Parents & 4Ps leaders by june 2021 | some 4P's Leaders & other Brgy. Officials were aware of their roles & responsibilities as parents | 114473 | 54031 | 47%
RPS & PES Training
Limited opportunities for men particularly fathers to participate in community based session in family |  |  | Organization & conduct of ERPAT Tarining | 50 LGU Employees(Fathers) & Brgy. Officials May 20020
12. Lack of GAD mechanism & institutions which addressed women and their children practical startegic needs. | To provide FA to partners & institutions providing services to VAW victims & vulnerable women & their children | Social Welfare and Development Programs | Provision of FA to partners, institutions, which caters abused women and their children | Financial Assistance to partners institutions was extended by end of Dec. 2021 | partner institutions were able to received the financial counterpart from the LGU | 75000 | 37000 | 49%
13. Need to intensify the support to Day Care service program for children 0-4 yrs old. | To improve the structure of Day Care Centers in identified brgys. | Social Welfare and Development Programs | Enhancement/improvement of 5 Day Care Centers | 5 Day Care Centers of Pandanon,Luyang, Naasog, Pantao II, Tampa, Inapoy & Dahile before Dec. 2021. | on procurement process
| To provide support to DCCs thru the provision of supplies & learning materials |  | Purchase of DCC supplies & learning materials | Provided supplies & other learning materials for DCCs in 32 Brgys | DCC's catering our 0-4 childred received learning supplies & materials | 100000 | 97011 | 97%
14. Improvement/enhancement & full operation of temporary crisis center for domestic violence & sexually abused survivors. | To have a fully functional Temporary Crisis Center | Social Welfare and Development Programs | Improvement of Crisis Center: | 50 VAW victims targetted per year before the end of Dec. 2021 | on procurement process | 200000 | 0 | 0%
Ceiling & repainting
water & electricity
additional rooms w/ CR
Fencing
15.Inadequate knowledge of parent & student leaders about GAD Laws, policies, issues and concerns. | To conduct training among parent & student leaders of 2 clustered educational institutions of Mabinay 3 & 4. | Capability Building | Conduct training workshop for parent & student leaders on GAD Laws, policies, issues & concerns. | 80 parent leaders & student leaders trained on GAD Laws, policies, issues & concerns by the end of July 2021. | 40 attended the said training on GAD related Laws | 100000 | 42075.65 | 42%
16. 885 Women in 298 households in Brgys. Poblacion, Dahile & Pandanon spend most of their time fetching water from a distance then spending it for livelihood activities. | To unload women of physical burden and manage their time in order to attend to livelihood activities to augment family income. | Provision of polythelene hose | Provision of polythelene hose to indentified households | 298 household provided 20 meters or more polythelene hose each by the end of Dec. 2021. | 97% implemented | 1200000 | 1165275 | 97%
Sub-total A | [5 empty] | 6539473 | 3011931.15 | 46.06%
ORGANIZATION-FOCUSED
1. Regular employees are incapable of addressing GAD issues & concerns due to lack of training on Gender sensitivity, mainstreaming & other GAD related laws & policies. | To capacitate employees who are regular, plantilla & job order positions about Gender & Development in the different offices of the LGU | Capability Building | Conducting GST Training workshop for LGU employees w/ regular plantilla & job order position | 95 male & 105 female employees trained in separate batches by the end of April 2021 | unimplemented due to pandemic | 50000 | 0 | 0%
2. Monetoring of the Functionality of GAD & VAW Desk in every Barangays | GAD Mandate | GAD and VAW Desk Functionality | Purchase of motor vehicle (XRM 125) | 32 Brgys monitored on GAD and VAW Desk by May 2021. | 84% implemented and 32 Brgys. Were being monitored | 90000 | 75400 | 84%
3. Unsatisfied level of awareness & understanding on GAD issues & concern & legal mandates among members of GFPS | To increase level of awareness & understanding of GAD issues, concerns & laws among members of GFPS | Capability Building | Participation/attendabnce in GAD trainings/seminars & conferences | GFPS members capacitated and fully aware & understand legal mandates on GAD by end of Aug. 2021 | not implemented due to pandemic restrictions | 300000 | 16360 | 5%
4. Construction of Women's Quarter Phase 2 at NORSU Mabinay | HGDG |  |  |  | for bidding process | 1500000 | 0 | 0%
Sub-total B | [5 empty] | 1940000 | 91760 | 4.73%
ATTRIBUTED PROGRAMS
Title of LGU Program or Project (10) |  |  |  |  | HGDG PIMME/ FIMME Score (11) | Total Annual Program/ Project Cost or Expenditure (12) | GAD Attributed Program/Project Cost or Expenditure (13) | Variance or Remarks (14)
Sub-total C
Grand TOTAL (A+B+C) | [5 empty] | 8479473 | 3103691.15 | 36.6%
Prepared by: (SGD) MELBA R. ABRIL Chairperson, GFPS TWG |  | Prepared by: (SGD) JOETERRY A. UY, MPA Local Chief Executive |  |  |  | DATE: 8/04/2022 DD/MM/YEAR