## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS
FOURTH QUARTER, CY -2021
Province, City or Municipality: Mabinay
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development (pls list down specific projects)
1. Counterpart fund for KALAHI-CIDDS Community based Response to COVID-19 |  | 4800000
2.Improvement of water supply system at Sitio Ibulan Paniabonan |  | 250000
3. Various waterworks system |  | 2000000 |  |  | 6.07% | 121445
Economic Development (pls list down specific projects)
4. Counterpart for PAGBAG-O waterworks and Agro-Forestry Projects |  | 500000
5. Various Electrification Projects |  | 2000000 |  |  | 8.96% | 179246
6. Road Conreting at Proper Brgy. Abis |  | 1000000 |  |  | 99.67% | 996730.3
7. Loan Amortization |  | 23967222.83 |  |  | 84.75% | 20311317.22
8. Concreting of Road at North Poblacion Cemetery |  | 2000000 |  |  | 99.84% | 1996890
9. Concreting of Access Road at Mabinay Spring |  | 1000000
10. Concreting of FMR at Sitio Basio, Lamdas |  | 1000000 |  |  | 99.84% | 998418.88
11. Concreting of Road at Sitio Camino Brgy. Samac |  | 1000000 |  |  |  | 0
12. Concreting of Mun.St. at Brgy. Poblacion in Camanche st. |  | 1000000 |  |  | 99.85% | 998483.94
13. Concreting of FMR at Sitio Lapong, Daheli |  | 1000000 |  |  | 99.7% | 996990.28
14. Rehabilitation of FMR at various sitios of Brgy. Mayaposi |  | 1000000
15. Rehabilitation of FMR at Sitio Pansalagon, Tara |  | 1000000 |  |  | 99.7% | 996996.28
16. Rehabilitation of FMR at Brgy. Napasu-an to Bugnay to Bulibulihan |  | 764257
17. Counterpart to TUBORAN Foundation for water System at Purok 1, Old Namangka |  | 100000
18. Road Opening fo 46th Street |  | 1000000
19. Concreting fo FMR at Brgy. Lumbangan |  | 1000000
20. Concreting of FMR at Brgy. Arebasore to Barras |  | 1000000 |  |  | 99.85% | 998463.96
21. Concreting of Access Road at Tie-land Village |  | 1000000 |  |  | 99.69% | 996930.24
22. Concreting of FMR t Brgy. Pandnon |  | 1000000 |  |  | 99.85% | 998493.6
23. Road Concreting at SweetSirland Village |  | 1000000 |  |  | 99.84% | 998403.44
GENERAL SERVICES
24. Imp. Of Multi-purpose Bldg. at Brgy. Pantao |  | 300000
25. Imp.of Multi-purpose Hall at Old Namangka |  | 500000
26. Dev't. of North Poblacion Cemetery |  | 543874.17
Environmental Management (pls list down specific projects)
Total |  | 51725354 |  |  |  | 31588809.14
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| (SGD) |  |  |  |  | (SGD)
MERIAM N. CADAYDAY |  |  |  |  | JOETERRY A. UY, MPA
Local Budget Officer |  |  |  |  | Local Chief Executive